## iOS Customer Part.
Sr.No. | Defects | Images to Refer | Type | Comments | Assigned to | Dev Status | QA Status | QA Comments | Images to Verify | Post Dev Status | QA Re-Test | Images to Re-Verify
B.O.D_001 | Go to iOS App Click On Explore our Services->Click On Continue->Accept terms & Condition->Click on Continue->Enter Details Click On Continue->Congratulations Pop Up Screen 'Successfully should be in Between | https://i.postimg.cc/4xT2bXdg/image.png | UI |  | Joydeep
B.O.D_002 | Go to iOS App Click On Explore our Services->Click On Continue->Accept terms & Condition->Click on Continue->Phone Number Should not accept more that 15 digits | https://i.postimg.cc/MK1f25pw/image.png | Functional |  | Joydeep | Solved | Done |  | https://i.postimg.cc/XJTKPwgv/image.png
B.O.D_003 | Go to iOS App ->Log In to Continue->Click On Profile->Click on Account info->Update the SSN field->Click On Update->Issue Showing Parse error. | https://i.postimg.cc/65FBf4sm/image.png | Functional |  | Joydeep | Solved | Done |  | https://i.postimg.cc/Z5ZGgNfj/image.png https://i.postimg.cc/FKYDnsQD/image.png
B.O.D_004 | Go to iOS App ->Log In to Continue->Click On Profile->Click on Account info->Password Field is showing lots of data. | https://i.postimg.cc/K8LZYPq5/image.png | Functional |  | Joydeep | Password is Converted in md5 format. In this cause password field showing lots of data | Done | As Discussed Password Is Converted in md5 Format.
B.O.D_005 | Go to iOS App Click On Explore our Services->Click On Continue->Accept terms & Condition->Click on Continue->Phone Number Should not accept Alphabets. | https://i.postimg.cc/K8LZYPq5/image.png | Functional |  | Joydeep | Solved | Done |  | https://i.postimg.cc/zDSxVQDD/image.png
B.O.D_006 | Go to iOS App ->Log In to Continue->Click On Profile->Click on Account info->Password Field Click On Change Button->Click On Change Passwords (Without enetering any values)->Showing "Enter New Password Pop Up->Issue User Should View "Enter Old Password". | https://i.postimg.cc/d0NnSxrs/image.png | Functional |  | Joydeep | Solved | Re Open |  | https://i.postimg.cc/MG79V30Y/image.png | Solved | Done | https://i.postimg.cc/26Zqyhtq/image.png
B.O.D_007 | Go to iOS App ->Log In to Continue->Click On Profile->Click on Account info->View Camera Icon->Issue Camera Icon Is Not Properly aligned | https://i.postimg.cc/MpSQqmqy/image.png | UI |  | Joydeep | Solved | Done |  | https://i.postimg.cc/Kck9x54Q/image.png
B.O.D_008 | Go to iOS App ->Log In to Continue->Click On Profile->Click on Account info->Click On Camera Icon->Click On Use Camera->Issue app is getting Collapased. |  | Functional |  | Joydeep
B.O.D_009 | Go to iOS App ->Log In to Continue->Click On Profile->Issue Image is Too small. | https://i.postimg.cc/vTCScS38/image.png | UI |  | Joydeep | Solved | Done |  | https://i.postimg.cc/htTL5CyQ/image.png
B.O.D_010 | Go to iOS App ->Log In to Continue->Click On Beauty & Services TAB->Issue listed Services is Showing all different colour combination. | https://i.postimg.cc/rsnXwJtQ/image.png https://i.postimg.cc/sxgMBKx8/image.png | UI |  | Subhomoy | Colors are come from API
B.O.D_011 | Go to iOS App ->Log In to Continue->Click On Beauty & Services TAB->Click On any Listed Service->Click On the Service ->Click On Listed Specialist->Click On View details->Issue Showing "Undefined is not a Object" & the screen goes blank. | https://i.postimg.cc/y6T5nTnk/image.png | Functional |  | Joydeep
B.O.D_012 | Go to iOS App ->Log In to Continue->Click On Beauty & Services TAB->Click On any Listed Service->Click On the Service ->Click On Listed Specialist->Click On Favourite Icon->Issue Service is not getting marked as Favourite. |  | Functional |  | Joydeep | API not done
B.O.D_013 | Go to iOS App ->Log In to Continue->Click On Beauty & Services TAB->Click On any Listed Service->Click On the Service ->View On Listed Specialist->Click On Map View Icon->Issue App is getting Crashed |  | Functional |  | Joydeep |  | Need API key for the iOS SDK for Google Maps
B.O.D_014 | Go to iOS App ->Log In to Continue->Click On Beauty & Services TAB->Click On Hair TAB->Click On the Cut / Style ->Click On Sort->Sort by 'Price-Low to High'->Issue not displaying High Listed Service. | https://i.postimg.cc/QMy5jvXH/image.png https://i.postimg.cc/90GJRcMx/image.png | Functional |  | Joydeep | Solved | Done |  | https://i.postimg.cc/k5WTWM3Z/image.png
B.O.D_015 | Go to iOS App ->Log In to Continue->Click On Beauty & Services TAB->Click On Hair TAB->Click On the Cut / Style ->Click On Filter->Issue Filter Icon Is Not Working "Not Clickable". |  | Functional |  | Joydeep | API not done
B.O.D_016 | Go to iOS App ->Log In to Continue->Click On Beauty & Services TAB->Click On Hair/any TAB->Click On the Cut / Style ->View All of the listed Services Outline Border is not visible | https://i.postimg.cc/4xSVGnbz/image.png | UI |  | Joydeep | Solved | If the specialist is black owned then the border shown in black , if the specialist is VIP then border shown in Pink color otherwise border is not visiable
B.O.D_017 | Go to iOS App ->Log In to Continue->Click On Profile->Click on Payment Methods->Issue Payment Method is not Clickable. |  | Functional |  | Joydeep | API not done
B.O.D_018 | Go to iOS App ->Log In to Continue->Click On Profile->Click on WishList->Click On Delete Icon->Issue Delete Icon Is Not Clickable. |  | Functional |  | Joydeep | Solved | Done |  | https://i.postimg.cc/TPkBKYV6/image.png
B.O.D_019 | Go to iOS App ->Log In to Continue->Click On Profile->Click on WishList->Click On View List->Issue View Details is Not Redirectable. |  | Functional |  | Joydeep | Solved | Re Open |  | https://i.postimg.cc/XJkVs1z8/image.png
B.O.D_020 | Go to iOS App ->Log In to Continue->Click On Profile->Click on Saved Address->Click On Add New->Enter Whole Details->Issue Street Address Field is Not clickable. | https://i.postimg.cc/vmxfX9x4/image.png | Functional |  | Joydeep | Solved |  |  | https://i.postimg.cc/2SrXxxFD/image.png
B.O.D_021 | Go to iOS App ->Log In to Continue->Click On Profile->Click on Notifications TAB-> Notifications Tab is not Clickable. | https://i.postimg.cc/L4GtYxJr/image.png | Functional |  | Joydeep | API not done
B.O.D_022 | Go to iOS App ->Log In to Continue->Click On Profile->Click on Get in Touch TAB-> Enter Details->Phone No Field Should Not accept Only '0' & let the Users click On Send Message. | https://i.postimg.cc/52rbbQ7q/image.png https://i.postimg.cc/g035Qxf0/image.png | Functional |  | Joydeep | Solved | Done |  | https://i.postimg.cc/FsCX18X6/image.png
B.O.D_023 | Go to iOS App ->Log In to Continue->Click On Profile->Click on Get in Touch TAB-> Enter Details->Phone No Field Should Not accept more than 15 digits. | https://i.postimg.cc/g035Qxf0/image.png | Functional |  | Joydeep | Solved | Done |  | https://i.postimg.cc/ydxT62CQ/image.png
B.O.D_024 | Go to iOS App ->Log In to Continue->Click On Profile->Click on Account Info>View SSN Field (Design Dosent Content SSN field) | https://i.postimg.cc/qqdnD2mM/image.png https://i.postimg.cc/tJ51rwZ2/image.png | UI |  | Subhomoy
B.O.D_025 | Go to iOS App->Click On forget Password->Enter Mail->Click On Send Button->Issue OTP is not getting received. | https://i.postimg.cc/YqV3QDgQ/image.png | Functional |  | Subhomoy
B.O.D_026 | Go to iOS App->Click OnExplore our Service->View Introduction / Terms & Policy-> Pattern should be proper. | https://i.postimg.cc/wBgPyxS1/image.png | UI |  | Joydeep
B.O.D_027 | Go to iOS App->Click OnExplore our Service->Enter details->Enter '0' as a Password->Issue Only "0" Cant be a Password |  | Functional |  | Joydeep
B.O.D_028 | Go to iOS App->Click On Gift card TAB->Issue Buy Now Button Is Not redirecting to any screen |  | Functional |  | Joydeep | API Not Done
B.O.D_029 | Go to iOS App->Click On Explore Our Services->Enter details & login with the account->Click On Profile->Click Accnt Info->Change the Password & Enter value in SSN Field->Click Update->Showing Error Message. | https://i.postimg.cc/W33XPdkP/image.png | Functional |  | Joydeep | Solved | Done |  | https://i.postimg.cc/mrRj4Z6W/image.png
B.O.D_030 | Go to iOS App ->Log In to Continue->Click On Profile->Click on Saved Address->Click On Add New->Location Title fields are accepting Imoji | https://i.postimg.cc/fWFtCVW0/image.png | Functional |  | Joydeep | Solved | Re Open | Add Address ->Location Title field is accepting Emoji field. | https://i.postimg.cc/JzwVbJt3/image.png
B.O.D_031 | Go to iOS App ->Log In to Continue->Click On Profile->Click on Saved Address->Click On Add New->Postal Code fields are accepting Imoji | https://i.postimg.cc/263zPxjF/image.png | Functional |  | Joydeep | Solved | Done |  | https://i.postimg.cc/JzwVbJt3/image.png
B.O.D_032 | Go to iOS App Click On Explore our Services->Click On Continue->Accept terms & Condition->Click on Continue->Validation Message for Wrong Email ID should not show ' . ' twice. | https://i.postimg.cc/Gh0pNBP5/image.png | UI |  | Joydeep | Solved | Done |  | https://i.postimg.cc/C1KKntx6/image.png
B.O.D_033 | Go to iOS App ->Log In to Continue->Click On Profile->Click on Account info->Password Field Click On Change Button->Click On Change Passwords (By enetering same values as Old Password)->Showing "Something Went Wrong" Pop Up->Issue User Should View "Something Went Wrong". | https://i.postimg.cc/ncPJsrT1/image.png | Functional |  | Joydeep | Solved | Re Open | Showing "Something Went Wrong" | https://i.postimg.cc/Ss1qHfpX/image.png
B.O.D_034 | Go to iOS App ->Log In to Continue->Click On Profile->Click on Account info->Update the SSN field->Issue SSN Field should Accept only 9 words. | https://i.postimg.cc/W3vBgJQQ/image.png | Functional |  | Joydeep | Solved | Done |  | https://i.postimg.cc/GtJ0dFWJ/image.png
B.O.D_035 | Go to iOS App ->Log In to Continue->Click on Beauty Products->Click On Eye Tab ->Click on a Product->Click On Add to Cart->View Drop down for Select Colour & size->Issue View Drop down is not getting displayed. | https://i.postimg.cc/YqRkBdYP/image.png | Functional |  | Joydeep | Solved | Done | Pleaser Kindly have a look into the Add to cart as of due to it cant test 1) Calculate Price (which is depending upon Color and Size), 2) Cart Updating, 3) Remove from Cart, 4) Place Order, 5) Order Confirmation | https://i.postimg.cc/C1cDtX1j/image.png
B.O.D_036 | Go to iOS App ->Log In to Continue->Click On Profile->Click on Saved Address->Click On Add New->Enter Whole Details->Issue pin Should not accept alpha Numeric digits | https://i.postimg.cc/sgg4XH4v/image.png | Functional
B.O.D_037 | Go to iOS App ->Log In to Continue->Click on Beauty Products->Click On Eye Tab ->Click on a Product->Click On Add to Cart->View Drop down for Select Colour & size->Select Quantity->Issue In Quantity Field User is able to add 0 qauantity of product. | https://i.postimg.cc/prYd4nk3/image.png | Functional
B.O.D_038 | Go to iOS App ->Log In to Continue->Click on Beauty Products->Click On Eye Tab ->Click on a Product->Click On Add to Cart->View Drop down for Select Colour & size->Select Quantity->Add to cart ->Issue Quantity button for increase & Decrease is not Proper. | https://i.postimg.cc/pTNvYLx7/image.png | Functional
B.O.D_039 | Go to iOS App ->Log In to Continue->Click on Beauty Products->Click On Eye Tab ->Click on a Product->Click On Add to Cart->View Drop down for Select Colour & size->Select Quantity in 8 digits ->Add to cart ->Issue Service Name is getting Overlapped | https://i.postimg.cc/prYd4nk3/image.png | Functional
B.O.D_040 | Go to iOS App ->Log In to Continue->Click on Beauty Products->Click On Eye Tab ->Click on a Product->Click On Add to Cart->View Drop down for Select Colour & size->Select Quantity->Review Order Screen->Issue Apply Button is getting Overlapped with the field. | https://i.postimg.cc/5NVFx8YH/image.png | Functional
B.O.D_041
B.O.D_042

## iOS Provider Part.
Sr.No. | Defects | Images to Refer | Type | Comments | Assigned to | Dev Status | QA Status | QA Comments | Images to Verify | Post Dev Status | QA Re-Test
B.O.D_001 | Go to iOS App Click On Register a Profession->Click On Continues->Enter details in List your Buisness screen ->Click on Sign up->Choose a Plan->Enter details in setup your payment screen-Click On Start Membership->Showing error Message. | https://i.postimg.cc/4xT2bXdg/image.png | Functional
B.O.D_002 | Go to iOS App-> Log in to the App->View Set Your Presence Toggle Button is Not Showing Proper. | https://i.postimg.cc/rpzxqsT1/image.png | UI
B.O.D_003 | Go to iOS App-> Log in to the App->Click On Buisness Info Upload Icon Is Not displayed. | https://i.postimg.cc/WzWL05Dq/image.png | UI |  |  | Upload Icon is only display when their are no image available | Done as Commented | Done as Commented
B.O.D_004 | Go to iOS App-> Log in to the App->Click On Buisness Info ->Issue Submit Icon Is Getting Displayed ->User Should View Update Icon. | https://i.postimg.cc/WzWL05Dq/image.png | UI |  |  | Solved | Done. |  | https://i.postimg.cc/HkDqLfLX/image.png
B.O.D_005 | Go to iOS App-> Log in to the App->Click On Employee ->Add New ->First name & Last Name Field Should not accept Digits. | https://i.postimg.cc/wjbdK0gj/image.png | Functional |  |  | Sloved | Done. |  | https://i.postimg.cc/7ZJSKW1s/image.png
B.O.D_006 | Go to iOS App-> Log in to the App->Click On Employee ->Add New ->First name & Last Name,SSN Field Should not accept Only Space. | https://i.postimg.cc/8PNqYqQS/image.png | Functional |  |  | Solved | Done. |  | https://i.postimg.cc/8knFxbzq/image.png
B.O.D_007 | Go to iOS App-> Log in to the App->Click On Employee ->Add New ->Mobile No Field Should not accept Only "0". | https://i.postimg.cc/8PNqYqQS/image.png | Functional
B.O.D_008 | Go to iOS App-> Log in to the App->Click On Employee ->Edit employee ->Issue Upload Photo Icon is not displayed. | https://i.postimg.cc/L5809gt3/image.png | UI |  |  | Upload Icon is only display when their are no image available
B.O.D_009 | Go to iOS App-> Log in to the App->Click On Employee ->Edit employee ->Issue Its should Be Update Icon Instead Of Submit. | https://i.postimg.cc/L5809gt3/image.png | UI |  |  | Solved | Done |  | https://i.postimg.cc/tghSMTdM/image.png
B.O.D_010 | Go to iOS App-> Log in to the App->Click On Employee ->Add New ->Enter Maximum 15 digits in Mobile No Field->Click On Save->View Employee List screen->Issue Mobile no is getting Overlapped over Edit & Delete Icon. | https://i.postimg.cc/Bn9kDb44/image.png | Functional |  |  | Solved | Done |  | https://i.postimg.cc/BZDT5ygm/image.png
B.O.D_011 | Go to iOS App-> Log in to the app->Click On Availability ->Add New ->Issue None of the feild is clickable. | https://i.postimg.cc/d1JKCBP2/image.png | Functional |  |  | Solved | Not-Done | Issue Clicking on it app is Getting Chrashed
B.O.D_012 | Go to iOS App-> Log in to the App->Click On Payment Info ->Click On Submit->Issue Showing Payment Failed | https://i.postimg.cc/BbBWnPwh/image.png | Functional | Subhomoy |  | Need to check API response message | You need to change some data before update other wise it will show Payment faield
B.O.D_013 | Go to iOS App-> Log in to the App->Click On Change Intro video->Click On Load From Library->Issue No Video Is Getting Updated. |  | Functional
B.O.D_014 | Go to iOS App-> Log in to the App->Click On Change Intro video->Click On Camera->Issue App Is Getting Chrashed. |  | Functional
B.O.D_015 | Go to iOS App-> Log in to the App->Click On Discount TAB->Add New->Add space In Title & Code Field & '0' Discount Type-> CLick On Submit->Issue Only Space & '0" should Not accept. | https://i.postimg.cc/Vk0NYmc3/image.png | Functional |  |  | Solved | Done. |  | https://i.postimg.cc/NGJKHxhd/image.png https://i.postimg.cc/sDPDJPbF/image.png https://i.postimg.cc/YqvzG9Pm/image.png
B.O.D_016 | Go to iOS App-> Log in to the App->Click On Discount TAB->Edit New->Add alphanumeric characters In Title Field & Code Field -> Click On Submit->Issue alpha Numeric Character should Not get accepted. | https://i.postimg.cc/cLfN9HW4/image.png | Functional |  |  | Solved | Not-Done | App is getting Chrashed.
B.O.D_017 | Go to iOS App-> Log in to the App->Click On Services TAB->Add New->Click On Sub-Category Pop Up Screen->Issue Pop Up Screen Is Displaying Half & not Showing data. | https://i.postimg.cc/gjqGw200/image.png | Functional |  |  | Solved | First you need to select the category after that the sub category data will be showing otherwise not and also some category don't have sub-category. so, on this time sub-category data not showing | As Discussed. | https://i.postimg.cc/BQwPrfJ5/image.png
B.O.D_018 | Go to iOS App-> Log in to the App->Click On Services TAB->Add New->Per Session Price field should not accept only '0'. | https://i.postimg.cc/hvjfqmsB/image.png | Functional |  |  | Solved | Not Done | As Discussed. | https://i.postimg.cc/SNQtZCK2/image.png
B.O.D_019 | Go to iOS App-> Log in to the App->Click On Images & Video TAB. ->Add New->Click On Submit->View in List of Images its getting overlapsed. | https://i.postimg.cc/cCzYkWY0/image.png | Functional
B.O.D_020 | Go to iOS App-> Log in to the App->Click On Images & Video TAB. ->Add New->Use Camera->App is getting Over lapsed. |  | UI
B.O.D_021 | Go to iOS App-> Log in to the App->Click On Service Slot. ->Add New->From Time & To Time Field is not accepting data. |  | Functional |  |  | Solved |  |  | https://i.postimg.cc/g2tVY6d7/image.png
B.O.D_022 | Go to iOS App-> Log in to the App->Click On Service Slot. ->Edit Slot->From Time & To Time Field is not accepting data. |  | Functional |  |  | Solved |  |  | https://i.postimg.cc/qMPtQXJ4/image.png
B.O.D_023 | GO to App->Register a new Professional->Add Employee->Adderess Field is Not accepting Data. |  | Functional

## Android Customer
Sr.No. | Defects | Images to Refer | Type | Comments | Assigned to | Dev Status | QA Status | QA Comments | Images to Verify
B.O.D_001 | Go to android App ->Log In to Continue->Click On Profile->Click on Account info->Click On Camera Icon->Click On Use Camera->Issue app is getting Collapased. |  | Functional |  | Joydeep | Solved | Not Done | Onece getting started Press Back Button from camera getting App Collapswd
B.O.D_002 | Go to android App ->Log In to Continue->Click On Profile->Click on Account info->Enyter Details->Click On Update->Issue Notification Tab is Showing too Small. | https://i.postimg.cc/k4t88Qjq/image.png | UI
B.O.D_003 | Go to android App ->Log In to Continue->Click On Profile->Click on Account info->Password Field Click On Change Button->Click On Change Passwords (By enetering same values as Old Password)->Showing "Something Went Wrong" Pop Up->Issue User Should View "Something Went Wrong". | https://i.postimg.cc/3RBht6fB/image.png | Functional |  | Joydeep | Solved | Not Done |  | https://i.postimg.cc/pLbnZbxs/image.png
B.O.D_004 | Go to android App ->Log In to Continue->Click On Profile->Click on Account info->Password Field Click On Change Button->Click On Change Passwords (Without enetering any values)->Showing both "Enter New/old Password Pop Up->Issue User Should Only View "Enter Old Password". | https://i.postimg.cc/HLPMNZJQ/image.png | Functional |  | Joydeep | Solved | Done |  | https://i.postimg.cc/Zn6ykVx8/image.png
B.O.D_005 | Go to android App ->Log In to Continue->Click On Profile->Click on Account info->Update the SSN field->Issue SSN Field should Accept only 9 words. | https://i.postimg.cc/4N1f8YqG/image.png | Functional |  | Joydeep | Solved | Done |  | https://i.postimg.cc/mk3hphTV/image.png
B.O.D_006 | Go to android App ->Log In to Continue->Click On Beauty & Product TAB->Issue listed Product is Showing all different colour combination. | https://i.postimg.cc/Kzqc5jYf/image.png | UI |  | Subhomoy | Colors are Come from API
B.O.D_007 | Go to android App->Click On forget Password->Enter Mail->Click On Send Button->Issue OTP is not getting received. | https://i.postimg.cc/4yW8yCBm/image.png | Functional |  | Subhomoy | Need to Check API
B.O.D_008 | Go to android App->Click On Gift card TAB->Issue Buy Now Button Is Not redirecting to any screen |  | Functional |  |  | API not Done
B.O.D_009 | Go to Android app->Go to Service->View Details->Book Appointment->Click On Cut/Style->Choose slots->Book now->Review Booking screen is Showing Wrong Payble amount | https://i.postimg.cc/MTzB398D/image.png | Functional |  | Subhomoy | Need to Check API
B.O.D_010 | Go to Android app->Go to Service->View Details->Book Appointment->Click On Cut/Style or any->Choose slots->Book now->Review Booking screen->Apply Coupon in Cash Showing Wrong data Amount Payable amount. | https://i.postimg.cc/qMjXWhBr/image.png https://i.postimg.cc/wjDx7Jt8/image.png | Functional |  | Subhomoy | Need to Check API
B.O.D_011 | Go to Android app->Go to Service->View Details->Book Appointment->Click On Cut/Style or any->Choose slots->Book now->Review Booking screen->Apply Coupon in Percentage Showing Wrong data Amount Payable amount. | https://i.postimg.cc/wB7kH6fr/image.png https://i.postimg.cc/4NRZ9ypz/image.png | Functional |  | Subhomoy | Need to check API
B.O.D_012 | Go to Android app->Go to Service->View Details->Book Appointment->Click On Cut/Style or any->Choose slots->Book now->Review Booking screen->Make Payment in Cash/any->Click On Download Receipt->Issue Receipt is not getting downloaded | https://i.postimg.cc/4xvsQ9z6/image.png | Functional |  |  | API not done
B.O.D_013 | Go to android app->Go to Cart->View added Products while ther is more than 1 ->1'st Product is Not Properly alighned. | https://i.postimg.cc/W4w27kPR/image.png | UI |  | Joydeep | Solved | Done
B.O.D_014 | Go to android app->Go to Cart->View added Products->Quantity Should be in 4 digits ->Product is Not Properly alighned. | https://i.postimg.cc/1tN4rzMD/image.png | UI |  | Joydeep | Solved | Not-Dnoe | https://i.postimg.cc/Vs23D4h7/image.png
B.O.D_015 | Go to android App ->Log In to Continue->Click On Profile->Click on Get in Touch TAB-> Enter Details->Phone No Field Should Not accept Only '0' & let the Users click On Send Message. | https://i.postimg.cc/L8kHXmm3/image.png | Functional | Solved | Joydeep | Solved |  | https://i.postimg.cc/Xq6kyZ2g/image.png
B.O.D_016
B.O.D_017

## Android Provider
Sr.No. | Defects | Images to Refer | Type | Comments | Assigned to | Dev Status | QA Status | QA Comments | Images to Verify
B.O.D_001 | Go to android App->Click On Register as a Professional->Go to Terms & Conditions I Agree with radio button to accept Privacy Policy is Half Displayed. | https://i.postimg.cc/9QG9yx3t/image.png | UI |  | Joydeep | Solved | Done |  | https://i.postimg.cc/Zn0vnJmL/image.png
B.O.D_002 | Go to android App->Click On Register as a Professional->Go to Terms & Conditions->Set Up Your Payment-> Enter more than 7 digits in CVV field->Click on Start Membership->Showing JSON Phase Error | https://i.postimg.cc/VkXdT4FG/image.png | Functional |  | Joydeep | Solved | Done |  | https://i.postimg.cc/k507K9Wc/image.png
B.O.D_003 | Go to android App-> Log in to the App->Click On Buisness Info Upload Icon Is Not displayed. | https://i.postimg.cc/J0LsR25d/image.png | UI |  | Joydeep | Solved | Done |  | https://i.postimg.cc/TPLDTdRq/image.png
B.O.D_004 | Go to android App-> Log in to the App->Click On Employee Info->Add new->Phone No Field Should not accept more than 15 digits | https://i.postimg.cc/J0LsR25d/image.png | Functional |  | Joydeep | Solved | Done |  | https://i.postimg.cc/Bn8TncpK/image.png
B.O.D_005 | Go to android App-> Log in to the App->Click On Payment Info ->Click On Submit->Issue Showing Payment Failed | https://i.postimg.cc/j25DF7xM/image.png | Functional |  | Joydeep | Solved | Need to change some data otherwise it shows Payment Failed |  | https://i.postimg.cc/8s87k3bK/image.png
B.O.D_006 | Go to android App-> Log in to the App->Click On Change Intro video->Click On Load From Library->Issue No Video Is Getting Updated & app is also getting Chrashed |  | Functional
B.O.D_007 | Go to android App-> Log in to the App->Click On Images & videos->Click On Camera ->Issue app is getting Chrashed |  | Functional |  | Joydeep | Solved | Not Done
B.O.D_008 | Go to android App-> Log in to the App->Click On Services->Enter '0' in Per Session Price Field->Issue Only '0' Should not get accepted as a Price. | https://i.postimg.cc/WzhzsqDt/image.png | Functional |  | Joydeep | Solved | Not Done | Issue Clicking on Submit Button Page is not getting Redirected. | https://i.postimg.cc/LX3TdtBZ/image.png
B.O.D_009 | Go to Android App->Create a Professional->GO to the Set Up Your Payment Screen->Enter Details Accpect Terms & Condition Spelling Mistake. | https://i.postimg.cc/bwsxvc8g/image.png | UI
B.O.D_010
B.O.D_011
B.O.D_012
B.O.D_013
B.O.D_014
B.O.D_015
B.O.D_016