## Sheet1
Sr.No. | Defects | Images to Refer | Comments | Assigned to | Dev Status | Platform | QA Status | QA Comments | Images to Verify | Post Dev Status | QA Re-Test | Images to Re-Verify
P.A._001 | Admin Portal->Spelling Issue In Conference Module | https://i.postimg.cc/8krDCx0J/image.png |  |  |  | Admin/Backend
P.A._002 | Register New Account for Couch->Vwrify Email ->OTP Not Received. | https://i.postimg.cc/vmx5tZbR/image.png |  |  |  | FE Website
P.A._003 | Subscribe as a Coach ->Click On Parac Sport LLC->app is Showing Error |  |  |  |  | FE Website
P.A._004 | Login & click On Compare->Action ->Delete Icon Is Not Shoing Hover Icon. | https://i.postimg.cc/NG5NFmKD/image.png |  |  |  | FE Website
P.A._005 | Click On Comparison Group Name->Back Button Is Getting Over lapped | https://i.postimg.cc/W3Q0hDyY/image.png |  |  |  | FE Website
P.A._006 | Click On Comparison Group Name->Back Button & Select New Atthelete to Compare button ->Button UI is not proper. | https://i.postimg.cc/JhxTDQ36/image.png |  |  |  | FE Website
P.A._007 | Compare->Compare Group name->Compare Page->Select New athelete to Compare->Add athlete to compare Search Field is not working. | https://i.postimg.cc/F1tRy3b8/image.png |  |  |  | FE Website
P.A._008 | Click On Comparison Group Name->Back button ->Back Button should not have a Underline | https://i.postimg.cc/15cnG7TK/image.png |  |  |  | FE Website
P.A._009 | Notification Icon Is Not clickable & Not Showing Hyper icon | https://i.postimg.cc/yYMKN7nQ/image.png |  |  |  | FE Website
P.A._010 | Teaming Up Groups->Invite a link->Copy link->Copy the link->Link not getting copied. |  |  |  |  | FE Website
P.A._011 | Reverse looks Up ->Action icon hyperlink title is not getting displayed. | https://i.postimg.cc/qqBH6G5j/image.png |  |  |  | FE Website
P.A._012 | Event List Page->action Icon->Edit & delete icon is not showing hover text. | https://i.postimg.cc/3Ndgnsy6/image.png |  |  |  | FE Website
P.A._013 | Event list Page Add Event->Start & end date cant be Past dates. | https://i.postimg.cc/hvYGcjDD/image.png |  |  |  | FE Website
P.A._014
P.A._015
P.A._016